## Slide 1: Project Atlas
Programme kickoff: ERP modernisation
Kickoff meeting · 3 November 2026

## Slide 2: Why we are doing this
Overview
Scope
Timeline
Governance
Responsibilities
Budget
Next steps
Single source of truth
Replace legacy finance and supply systems with one cloud ERP
7 → 1
core systems
Faster financial close
Automate reconciliations and management reporting
−40%
month-end close time
Lower run cost
Retire on-premise infrastructure by 2028
$3.1M
annual savings

## Slide 3: What is in and out of scope
Overview
Scope
Timeline
Governance
Responsibilities
Budget
Next steps
In scope
Finance and accounting
Procurement and inventory
Order-to-cash
Data migration (5 years)
Training for 600 users
Out of scope
HR and payroll
Manufacturing execution
Customer portal changes
Legacy archive clean-up

## Slide 4: Delivery timeline, 2027
Overview
Scope
Timeline
Governance
Responsibilities
Budget
Next steps
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Discover
Design
Build
Test
Deploy
Hypercare
Design sign-off
Go-live
Milestones

## Slide 5: Governance and team structure
Overview
Scope
Timeline
Governance
Responsibilities
Budget
Next steps
Steering Committee
Monthly · CFO chair
Programme Director
A. Mehta
PMO
Weekly reporting
Finance
R. Iyer · 4 FTE
Supply chain
J. Costa · 4 FTE
Technology
L. Chen · 4 FTE
Workstream leads report weekly to the Programme Director; escalations go to the Steering Committee within 5 days.

## Slide 6: Roles and responsibilities (RACI)
Overview
Scope
Timeline
Governance
Responsibilities
Budget
Next steps
Activity | Sponsor | Director | Finance | Supply | IT
Approve budget | A | R | C | C | I
Define requirements | I | A | R | R | C
Configure system | I | A | C | C | R
Migrate data | I | A | R | R | R
User testing | I | A | R | R | C
Go-live decision | A | R | C | C | C
R
Responsible
A
Accountable
C
Consulted
I
Informed

## Slide 7: Budget: $8.6M over 18 months
Overview
Scope
Timeline
Governance
Responsibilities
Budget
Next steps
Chart: 
| Delivery partner | Software licences | Internal team | Training and change | Contingency
Budget | 3.1 | 2.9 | 1.5 | 0.6 | 0.5
$8.6M
total
Delivery partner
$3.1M
36%
Software licences
$2.9M
34%
Internal team
$1.5M
17%
Training and change
$0.6M
7%
Contingency
$0.5M
6%

## Slide 8: Next steps
Overview
Scope
Timeline
Governance
Responsibilities
Budget
Next steps
Confirm workstream leads and backfills
7 Nov
Sign implementation partner contract
14 Nov
Complete current-state process mapping
12 Dec
Steering Committee approves design scope
15 Jan
Questions?
Anika Mehta
Programme Director
atlas-pmo@company.com